## 00_Dashboard
A44 SAR ADC Project Tracker - Progress Tracking
Updated 2026-07-28 from the audited A44 R2 circuit/simulation package. PASS basis: FULL255 uses only Seed 44 TT; PVT is diagnostic-only.
|  |  | Rollup | Value |  | Legend
|  |  | Avg schematic progress |  |  | Done
|  |  | Avg layout progress |  |  | In progress
|  |  | Avg post-layout progress |  |  | In review
|  |  | Done items |  |  | Blocked
|  |  | In progress / planned |  |  | Planned
In review
Blocked
Hierarchy level | Cell / deliverable | Schematic-level design+sims | Layout | Post-layout sims | Status | Main evidence / open issue
0 | Project objective + frozen performance targets | 100% |  |  | Done | Frozen targets: 8-bit, 2 MS/s, 3.3 V fully differential GF180MCU SAR ADC; SNDR >= 44 dB, ENOB >= 7 bit, ¦DNL¦ < 1 LSB, ¦INL¦ < 1.5 LSB, zero missing codes and zero reversals for the governing static case.
0 | External functional interface | 100% |  |  | Done | Frozen normal interface: VDD, GND, VREFP, VREFN, VINP, VINN, CLKS and DOUT[7:0]; no normal READY, CONVST, VCM, CLKC or SAR_CLK.
0 | IDEAL SAR ADC golden functional reference | 100% |  |  | Done | Unified S4/S5 golden waveforms define correct sampling ownership, 8 CMPCK pulses, one-hot DCMP, D7→D0 decisions, 7 CDAC updates, residue settling and DOUT hold/update behavior.
1 | StrongARM comparator | 100% | 0% | 0% | Done | Current resized StrongARM .sch/.sym and extracted subcircuit are frozen in the R2 package. Schematic/source binding is audited; layout/PEX qualification is not claimed. Integrated performance is governed by rows 23 and 24.
1 | Bootstrap sampling switch | 100% | 0% | 0% | Done | Bootstrapped sampling path is verified in the actual CDAC behavior path and in integrated TOP operation.
1 | CDAC + bi-directional switching | 100% | 0% | 0% | Done | Active-low P/N selector order, bit-by-bit residue progression and S4/S5 behavior verified; around-zero S6 bounds the 127→128 transition to 0–0.25 LSB.
1 | Asynchronous SAR logic actual RTL / Magic PEX wrapper | 100% | 100% | 85% | In review | Actual asynchronous RTL and the accepted SS Magic PEX core/wrapper are bound into the current TOP. Deterministic 8-decision/7-update behavior is established, but this is not full-PVT or tapeout signoff.
2 | SAR_ADC_TOP closed-loop integration | 100% | 0% | 0% | Done | Actual comparator, CDACs and SAR-logic wrapper are assembled in the closed-loop TOP; the unified R6 load wrapper is used for PVT waveform tests.
2 | TOP RC load and PVT diagnostic execution | 100% | 0% | 0% | Done | PVT3 selected MC20 LOW/W4 completed 60/60: TT 19/20, SS 20/20, FF 20/20 hard-dynamic PASS. This population is diagnostic-only and is not a performance PASS, yield, promotion, or signoff basis.
2 | TOP static linearity verification | 100% | 0% | 0% | Done | FULL255 static qualification PASS is based only on S044_TT: max ¦DNL¦ = 0.610351 LSB, max ¦INL¦ = 0.686645 LSB, 0 missing codes, and 0 reversals. Other TT seeds and Seed 44 SS/FF curves are diagnostic-only; PVT cannot establish or overturn PASS.
2 | TOP dynamic spectral verification | 100% | 0% | 0% | Blocked | MC200 TT LOW/W4 execution completed 200/200: 197 hard-dynamic PASS and 3 FAIL (Seeds 65, 68, 141). SNDR P1/P5/P10/P50 = 46.8729/47.2961/47.4636/48.4065 dB. Execution is complete, but the unresolved hard failures keep performance at NO PROMOTION; PVT MC20 does not waive them.
3 | Die top: pads, ESD, supply/reference interface | 10% | 0% | 0% | Planned | ADC_DIE_TOP, pad/ESD integration, supply partitioning, reference decoupling and full-chip LVS-ready hierarchy remain to be implemented.
3 | Package / bondwire / PCB-level testbench | 25% | 0% | 0% | Planned | Equivalent lumped loads are defined and used for VIN, VREF, CLKS, DOUT and VDD/GND TOP tests; package, bondwire and complete PCB models remain pending.
4 | Full-chip signoff readiness | 15% | 0% | 0% | Blocked | Full-chip signoff remains blocked by the three MC200 hard-dynamic failures, analog/full-chip layout, DRC/LVS/PEX, final extracted regression, and package/board closure. FULL255 S044_TT passes; PVT results remain diagnostic-only.

## 01_Verification_Status
A44 R2 Verification Status and Governing PASS Basis
Updated 2026-07-28. Execution completeness, method/integrity PASS, performance PASS, promotion, and signoff are separate conclusions.
Evidence set | Role | Completion | Governing qualification basis | Current evidence | Disposition | Authoritative path
FULL255 static | Performance qualification | 6 unique curves; 1 governing | Seed 44 TT only (S044_TT). PVT and other TT seeds are diagnostic-only. | S044_TT: max ¦DNL¦ 0.610351 LSB; max ¦INL¦ 0.686645 LSB; missing 0; reversals 0. | PASS | verification/a44_r2/02_SIMULATION_RESULTS/03_FULL255_STATIC
MC200 TT LOW/W4 | Performance qualification | 200/200 | FAST64_SS_W4, TT/3.3 V/27 C, 50 ps, formal frames 4-67. Unresolved hard failures are not waived by PVT. | 197 hard-dynamic PASS; 3 FAIL: Seeds 65, 68, 141. | FAIL / NO PROMOTION | verification/a44_r2/02_SIMULATION_RESULTS/01_MC200_TT_LOW_W4
PVT3 selected MC20 LOW/W4 | Diagnostic | 60/60 | Diagnostic-only; not a PASS, yield, promotion, or signoff basis. | TT 19/20; SS 20/20; FF 20/20 hard-dynamic PASS. | DIAGNOSTIC ONLY | verification/a44_r2/02_SIMULATION_RESULTS/02_PVT3_MC20_LOW_W4
CACE preflight | Tool-chain verification | 1/1 | Validates the packaged Xschem-to-ngspice path; does not imply ADC performance PASS. | final_v = 1.250 V within 1.249-1.251 V. | PASS (METHOD) | verification/a44_r2/03_CACE_AND_SIMULATION_TOOLS
Quick reproducibility | Reproducibility | 130/130 | Exact reproduction of selected frozen comparisons; does not change performance disposition. | 25 MC200 + 75 PVT3 + 30 FULL255 records match. | PASS (REPRO) | verification/a44_r2/02_SIMULATION_RESULTS/06_RUN_OUTPUTS
Package manifest | Integrity | 4,846 records | File presence and SHA-256 equality only; not performance PASS. | Zero mismatches on fresh-checkout readback. | PASS (INTEGRITY) | verification/a44_r2/05_PACKAGE_AUDIT
Performance Snapshot
Metric | Value | Acceptance / interpretation | Qualification use
S044_TT max ¦DNL¦ | 0.61035 | < 1 LSB | Governing FULL255 PASS metric
S044_TT max ¦INL¦ | 0.68664 | < 1.5 LSB | Governing FULL255 PASS metric
S044_TT missing codes / reversals | 0 / 0 | 0 / 0 | Governing FULL255 PASS metric
MC200 hard-dynamic result | 197 PASS / 3 FAIL | No unresolved hard-dynamic failures | Current performance blocker
MC200 SNDR P1 / P5 / P10 / P50 | 46.8729 / 47.2961 / 47.4636 / 48.4065 dB | Population summary; percentiles do not override record failures | Supporting metric
PVT3 selected MC20 | TT 19/20; SS 20/20; FF 20/20 | Diagnostic-only | Not a PASS basis
Current project disposition: COMPLETE AS EXECUTED / PERFORMANCE FAIL / NO PROMOTION. The blocker is the three MC200 hard-dynamic failures. FULL255 passes on S044_TT; PVT is diagnostic-only. No layout, full-chip PEX, silicon, tapeout, or production-yield signoff is claimed.